## todo list
	Design the HTML templates: Create the index.html template and any other necessary HTML templates for registration, login, posts, comments, and private messages. Structure the templates with appropriate placeholders for dynamic content.
	Implement the database functionality:
	Set up the SQLite database and create the necessary tables (use migrations).
	Write the database connection code in db/database.go.
	Implement functions in db/database.go to handle database operations like user registration, login, post creation, comment creation, and message storage/retrieval.
	Handle registration and login:
	Implement the registration handler in handlers/auth.go to handle the form submission, validate the input, and store the user data in the database.
	Implement the login handler in handlers/auth.go to handle user authentication based on the nickname or email combined with the password.
	Implement post and comment functionality:
	Create the HTML form for creating posts in the index.html template.
	Implement the post creation handler in handlers/posts.go to handle the form submission, validate the input, and store the post data in the database.
	Design the frontend display for posts and comments using HTML and CSS.
	Implement the logic in handlers/posts.go to retrieve and display posts in the feed.
	Implement the comment creation handler in handlers/posts.go to handle comment submission and store the comment data in the database.
	Set up WebSocket connections:
	Create the JavaScript file static/main.js to handle WebSocket connections and events.
	Implement WebSocket connection handling in utils/websocket.go on the server-side.
	Establish WebSocket connections in the frontend using JavaScript and handle events like new message notifications, user status updates, and chat reloading.
	Private message functionality:
	Design the HTML layout for showing online/offline users and the chat window.
	Implement the logic in handlers/messages.go to handle private messages, including sending and storing messages in the database.
	Implement the functionality to display online/offline users and organize them based on the last message sent.
	Handle the click event on a user to reload past messages in the chat window.
	Implement message reloading functionality to fetch and display previous messages between users.
	Styling and CSS:
	Apply CSS styles to the HTML elements to enhance the visual appearance of the pages.
	Use CSS to stylize the elements of the chat window, online/offline user section, and other UI components.

	following is old do not use
3	create database when server starts	check if database already exists
1	server setup	create code to set up a server
2	create queries
4	database structure
4	database structure	create comments table	comments table will have fields:
4	database structure	create comments table	comment_id: uuid
4	database structure	create comments table	post_id: uuid
4	database structure	create comments table	user_id: uuid
4	database structure	create comments table	comment_content: varchar
4	database structure	create comments table	comment_date: real
4	database structure	create messages table	messages table will have fields:
4	database structure	create messages table	message_id: uuid
4	database structure	create messages table	user_id_from: uuid
4	database structure	create messages table	user_id_receiver: uuid
4	database structure	create messages table	message_content: varchar
4	database structure	create messages table	message_date: real
4	database structure	create posts table	posts table will have fields:
4	database structure	create posts table	post_id: uuid
4	database structure	create posts table	user_id: uuid
4	database structure	create posts table	post_category: varchar
4	database structure	create posts table	post_title: varchar
4	database structure	create posts table	post_created_date: real
4	database structure	create posts table	post_content: varchar
4	database structure	create sessions table	Add there fields to the table:
4	database structure	create sessions table	user_id: uuid
4	database structure	create sessions table	session_id: uuid
4	database structure	create sessions table	session_expiration: real
4	database structure	create users table	Table must contain fields:
4	database structure	create users table	ID: uuid
4	database structure	create users table	Nickname: varchar
4	database structure	create users table	Age: integer
4	database structure	create users table	Gender: varchar
4	database structure	create users table	First Name: text
4	database structure	create users table	Last Name: text
4	database structure	create users table	E-mail: text
4	database structure	create users table	Password: hash

## project tree
- jaava2
	- main.go
	- backend/
		- config/
			- db_connect.go
			- websocket.go
		- data/
			- register.go	-contains user struct and registerhandler
			- postdata.go
		- handlers/
			- handle_login.go
			- handle_logged.go
			- posts.go
			- messages.go	messages.go not made yet
		- rtlforum.db
		- rltforum.db
		- SQLite_rltforum.sql
	- clientfrontend/
		- static/
			- styles.css
			- registration.js
			- login.js
			- feed.js
			- post.js
			- comment.js
			- messages.js
			- main.js
		- templates/
			- index.html	only index should remain, currentli other html files displayed views in browser, but javascripts in static folders should now do this
	- .gitignore
	- go.mod
	- go.sum
	- README.md
	- jaava2 kava.ods			this is spreadsheet of project structure

Database
posts
	id	integer
	user_id	integer
	title	varchar
	text	varchar
	created_at	timestamp
	like	varchar	not used in real-time-forum
	dislike	varchar	not used in real-time-forum

user
	id
	nickname
	age
	gender
	firstName
	lastName
	email
	password
	sessionID

comments
	id
	user_id
	post_id
	text
	created_at

messages
	id
	sender_id
	receiver_id
	message
	created_at

	following is old, do not use

	backend
		data	comments.go	struct comment
				content
				insert comment
				get_comments	post_ID jne
		handlers
		main.go
	frontend	siin on variant kas teha	framework	siin on variant kas	vue
					react
					angular
			js
			html
			css

## soovitan oppida
1			go get -u github.com/mattn/go-sqlite3
2			go get golang.org/x/crypto
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85

			https://javascript.plainenglish.io/my-salary-increased-13-times-in-5-years-here-is-how-i-did-it-bb3a2a945037